## 一、project description
Project Summary
Project goal | 1. Based on the Chogori platform, a distributed memory Schema-aware KV (SKV) system, evaluate the system performance of the memory tiered architecture and make use of the SKV architecture. 2. Based on the evaluation result, design a efficient single-node full-memory index structure and study its application scenarios. 3. Based on the evaluation result, optimize the object storage system with the hybrid memory architecture and study its application scenarios. 4. Based on the SKV architecture, design the NDP operator acceleration system of the graph storage engine and study its application scenarios.
Project plan
System architecture
Biweekly Overall Progress（from Start - 2021.1.14）
Overall Progress： 1. Survey on the memory index, MVCC, page cache policies, and distributed transaction protocol; 2. Successfully deploy and run Chogori open source project; 3. Preliminarily understand and design how to find an empty slot for the hot row in the PBRB cache. 4. Preliminarily understand where and how index work in Chogori project. 5. Simply learn the plog design framework in chogori. 6. Investigate the data layout of graph and compare with SKV. 7. K23SI transaction optimization about write intent pending. Next Plan： 1. Following the indexer branch, (define a unified interface if necessary), implement the indexer module and integrate the hot trie index (Yirui Lai). 2. Implement important functions in PBRB: find empty slots, read/insert hot rows from/to PBRB, eviction policy, e.g., LRU, LIRS, 2Q (Qiang Zhang and Ruida Xu). 3. Research on persistent Memory and Plog (Zhen Liu) 4. K23SI transaction optimization (Zuo Shun) 5. Graph database survey (How to efficiently use SKV to represent graphs.)(Mingxiang Lu) 6. Implement K23SI transaction optimization schema(Zuo Shun)
Biweekly Overall Progress（from 2021.3.1 - 2021.3.14）
Overall Progress： 【Index】 1. Coding the detail impelmentation of index interface. 2. Survey on state-of-the-art in-memory index. 【PBRB】 1. Reorganize and improve the algorithm to find empty slots from PBRB. 2. Survey on the detail impelmentation of eviction policy in Redis. 【PLog】 1.Research papers based on PMM including index structure, kv optimization and file system areas. 2.Done some simple file benchmarks with NVM based on Ext4 file system under dax mode. 【Transaction】 1.Merge the optimization discussed before with the new optimized version in k23SI-Detailed-States. 【Graph】 1.Do research on the open source graph database.
Biweekly Overall Progress（from 2021.3.14 - 2021.3.30）
Overall Progress： 【Index】 1. coding to realize index leaf node keyValueNode cache multi-version information. 【PBRB】 1. working on cache write and eviction strategy coding, not yet integrated into the Chogori project. 【Transaction】 1. optimize the use of payload in some updates. 【PLog】 1.Test AEP reading and writing performance in a laboratory environment. 【Graph】 1.analyze several graph databases, focusing on nebula.
三、Risks & Call for help

## 二、Detailed Progress(TxnSystem)
二、Detailed Progress
System | Module | Task | Priority | Workload | responsible personality | Planned completion time | Completion time | Status | Details | Risks | Remarks
distributed transaction system | K23SI protocol | Understand the K23SI transaction protocol. And compares the protocol with spanner | high | big | Shun Zuo | 2020-12-27 | 2020-12-27 | finished | Spanner 和 K2 的不同点可以归纳为以下几点： 1. 一致性等级：Spanner 处于 lineraizability，该一致性更关心实时时间顺序，而 K2 则是处于 SC，只关注于所谓的 program order，当然，由于其独立性的限制，并不是所有的 SC 操作序列都可以出现在 K2 事务中 2. 并发控制：对于读写事务，Spanner 使用 2PL/PCC，而在 K2 中则是使用 WI-ReadCache/PCC 来控制并发 3. 单个写操作：对于单个的写操作而言，K2 会将每个写操作的数据迅速发送到相关的 Node 节点上，但是在 Spanner 中，写操作的数据会在最后跟随 Commit 请求一起提交。因此，在 Spanner 中，并不存在 read-own-write 特性（注意：可以改进 Spanner 相关协议，使得其支持该特性） 4. 提交协议：K2 使用的是 1PC，而 Spanner 使用的是改进过的 2PC 协议，在提交操作的时候，K2 需要更少的 RTT。
|  | Optimize the RetentionWindow to reduce the memory footprint of Multi-versioned records | low | medium | Shun Zuo | - |  | pending
|  | Optimize the WI of K23SI transaction.The server returns WI_persis_pending after writing WI in the memory | high | big | Shun Zuo | 2021-01-22 | 2021-01-29 | finished | 最终总结出来的方案如下（示意图在右边的单元格中）： 1. 不同于最开始的同步版本，现在客户端将 w_req 发送给对应的 participant，participant 立即返回 w_ack_pending 给客户端，从而允许客户端再次发送一个w_req 到另外一个 participant 上，从而实现异步发送写请求 2. 当我们采取这个异步写的优化方案的时候，我们就需要解决如何追踪对应 write key 的持久化信息，本方案中采用的是 TRH 来追踪这些持久化信息，当客户端发送 end_req 的时候将会附带该事务中的所有 writeKeys，TRH 从而可以对比自身追踪到和由客户端发送过来的 writeKeys 来判断是否所有的 wirte 操作都已经持久化，从而决定是 abort 客户端的 end_req
|  | Merge the optimization discussed before with the new version in K23SI-Detailed-States. | high | medium | Shun Zuo | 2021-03-19 | 2021-03-19 | finished | The integrated plan is shown on the right: 1. The client determines trh in the first write operation, and then every time a write request is sent to the participant, it needs to send an additional w_key_req request to trh to notify trh of the key value written by the current transaction, and the current write request of the client It contains the request id; 2. When the participant receives the w_req from the client, it immediately returns w_ack_pending to notify the client that the write request has been received and the persistence task is executed in the background. When the task is completed, it informs trh that the persistence is successful; 3. Trh needs to maintain a std::map<dto::Key, WriteKeyStatus> internally, which is used to track whether the key corresponding to the write request is persisted successfully. WriteKeyStatus records the request id corresponding to the last write request, and contains a boolean variable isPersisted used to indicate whether the persistence is successful; 4. When processing onEnd(C), trh needs to wait for a period of time to ensure that all write requests are persistently completed. If the waiting time exceeds the waiting time, abort. 5. Since trh can know in advance that those write requests have been persisted, when the transaction enters the ForceAbortedPIP state, the finalization (aborted) task can be executed in advance to improve the overall throughput of the system.
|  | Implementation of the updated optimization schema | high | big | Shun Zuo | 2021-03-31 |  | pending | Since the implementation task of the new transaction state machine is handed over to ivan, it will modify the relevant code in the process of implementing the state machine to support the optimization scheme. This part of the code will not be implemented for the time being. This part of the related code implementation ivan has submitted pr, and my current task is to understand and familiarize with the relevant content in its pr, such as the change of the state of the transaction state machine, the state machine transition condition, and the persistence of the transaction.
|  | Implement the copyToPayload method in Payload.cpp(mainly the issue #74) | low | medium | Shun Zuo | 2021-04-09 |  | ongoing | The current PartialUpdate method is implemented by constructing a complete record with known information, and then writing it into the memory. Since the two operations of payload reading and writing are involved in this process, the current implementation way is relatively ineffective. Therefore, we can directly implement the data copy operation between two payloads by adding a method copyToPayload to improve the execution efficiency of partial update. The work arrangement is as follows: First, implement the template method copyToPayload according to the existing code; then, transplant the partial update method (mainly involving the merging of data read and write operations) to improve its efficiency; finally, write some tests to verify the correctness of the code implementation.
|  | submit the pr of the implemented copyToPayload method | low | medium | Shun Zuo | 2021-04-14 |  | ongoing | The main task is to test the implemented copyToPayload method, and make it pass the test (mainly unit test and integration test), and submit pr after confirming that it is correct.

## 二、Detailed Progress(TieredMem)
二、Detailed Progress
System | Module | Task | Priority | Workload | responsible personality | Planned completion time | Completion time | Status | Details | Risks & d | Remarks
Distributed Tiered Memory Object System | Single-node full memory index research | survey on the proposed memory indexes and how they implement MVCC. | high | big | Yirui Lai | 2020-12-31 | 2020-12-31 | finished | 阅读内存索引相关论文：1. HOT（SIGMOD’18）为了提高前缀树索引的性能，提出了针对树高进行优化的策略，在此策略下使用多种方式实现一个对任何输入都保证树高在log(n)量级的前缀树，包括内部节点进行多个位同步比较、压缩搜索树路径、设计新的插入算法等。2. Fast Serializable Multi-Version Concurrency Control for Main-Memory Database Systems（SIGMOD’15）比较了当时常用的内存数据库中MVCC的实现方式，指出当时绝大多数MVCC系统是基于版本链设计，并针对不同的实现，分析了他们的性能。3. PTREES（PVLDB 19）提出了一种使用路径复制的全新MVCC实现方式，将版本数据与索引器结合，数据库的每一个版本对应索引器的树结构的一个root，直接从对应时间的root访问版本数据，相比版本链具有访问快速、无需追溯外存中版本链的优势。
|  | Design an unified interface for indexer | high | medium | Yirui Lai | 2021-01-29 | 2020-01-28 | finished | 在已有代码基础上，确定了使用keyvaluenode作为索引器存储的数据，keyvaluenode保存最近三个版本的数据指针，便于快速访问历史数据。
|  | optimize the version chain design | medium | medium | Yirui Lai | - |  | pending
|  | Integrate HOT index and map in the interface module | high | big | Yirui Lai | 2021-03-31 | 2021-04-02 | finished | Implementation of index interface and KeyValueNode module, following the doc in K2-RFC, temporarily store all value data in memory using "new" operation, modify code in module.cpp to use index interface.
|  | Test indexer module | high | medium | Yirui Lai | 2021-04-23 |  | ongoing | Design unit tests and document them. Writing unit tests for this part of the code, focus on the correctness of the three versions of the swap-in logic, the correctness of version chain access and memory management, the correctness of the indexer combined with the module .cpp code.
|  | testing system performance | high | medium | Yirui Lai | - |  | pending | Test system performance, compare the performance gap between std::map and HOT index. Need to start after unit test.
|  | 熟悉项目文档和代码 | high | medium | Chunyu Li | 2021-03-24 | 2021-03-24 | finished | 1. Getting familiar with the chogori architecture, read the design document, and with the code. Focus on the index part and its calling-context. 2. Assist Yirui in integrating the HOT index.
|  | Design test cases | high | medium | Chunyu Li | 2021-04-09 |  | Ongoing | Design test cases based on the implementation of HOT indexer
|  | Write and run tests | high | medium | Chunyu Li | 2021-04-23 |  | pending | 1.Write tests of HOT indexer and plan to finish before 4/19 2.Run unit tests and performance tests
| Page Based Row Buffer | Survey cache space dynamic allocation and management strategy | high | big | Qiang Zhang | 2020-12-31 | 2020-12-31 | finished | Papers about dynamic allocation and management of cache space：1.CloudCache(FAST'16):to share the host's memory between multiple applications, it proposes the RWS model based on WS model,it only caches the data that be accessed at least N times in a specified time, and allocate memory dynamically according to the amount of the data. So it can allocate memory for applications on-demanding according to the data access characteristics of applications, and avoid pollution of memory. 2. In order to accurately depict the memory requirements of the application, a common method is to draw the MRC curve, which shows the change of the cache miss rate as the cache capacity changes. However, the time and space cost of drawing the MRC curve is very large，SHARDS（FAST'15）designs a method of random spatial sampling to build MRC with low time and space overhead，and can guarantee high accuracy. Other related papers are OSCA(ATC'20),vCacheShare（ATC'14）
|  | Survey typical cache eviction policy | high | big | Ruida Xu,Qiang Zhang | 2020-12-31 | 2020-12-31 | finished | We have preliminarily understood the classical cache replacement strategy by reading papers (e.g., LRU,LIRS,ARC,2Q)：LRU kicks out a large number of hot data when performing range query that leads to memory pollution, LIRS designs a multi-level LRU queue. When the data is accessed for the first time, it will be put into the first-level LRU. When the data in the first-level LRU is hit, it will be moved to the second-level LRU, so as to avoid the impact of range query and other operations on the efficiency of cache. However, the size of the multistage LRU queue needs to be set in advance, which makes it less flexible. ARC has proposed a strategy that can adjust the size of the multistage LRU queue adaptively to different applications. The next step will be to investigate the improved cache replacement strategies presented in recent years（e.g., GDSF, adaptSize），and implement the classical eviction policy (LRU,LIRS）int PBRB.
|  | Design and implement the findEmptyRow() function in PBRB Cache | high | medium | Qiang Zhang, Ruida Xu | 2021-01-29 | 2020-01-28 | finished | The KVNode in the indexer is required to provide some function interfaces, such as the number of hot versions in KVNode, the neighbors of KVNode, etc.
|  | Survey on implement of cache eviction policy in typical memory Key-Value storage system (e.g. Redis) | high | medium | Ruida Xu, Qiang Zhang | 2021-02-06 |  | finished | Research Redis, Memcached and other typical kv system memory cache eviction policy. The eviction policy of Redis is reviewed in detail, and the specific eviction method is as follows: When the amount of memory used is greater than the maximum memory capacity specified by the user, Redis randomly selects a few (default 5) keys for comparison by sampling, and swaps out the oldest key-value pair, thus approximating the LRU algorithm; In Redis 3.0 and later versions, Redis has added a buffer pool (the default size is 16 keys) to buffer its swapped keys to improve its approximate LRU performance, and improve the accuracy of LRU with little time overhead. In the Chogori platform, when the PBRB Page usage is large and needs to be recycled, we can also use the sampling method as a way to recycle the keys in the memory.
|  | Discuss and improve the findEmptySlots algorithm in detail | high | medium | Qiang Zhang, Ruida Xu | 2021-03-01 | 2020-03-05 | finished | When selecting empty slots from the PBRB cache, it is necessary to maintain the order of rows between pages and within pages as much as possible to improve the hit rate of the CPU cache, which is mainly discussed in the following two cases: 1. When the SKV has previously cached several versions, in order to limit the number of versions cached to limit memory overhead, always choose the version with the oldest or expired timestamp to be evicted first, and then store the version that needs to be cached in the location of the evicted version. 2. When the SKV cached for the first time, that is, not be cached version before, we determine the location of the SKV according to the adjacent key location, adjacent and cached SKV key can be obtained from the index, we can query the left and right neighbors of the SKV with the help of the indxer: if the two address belonging to the same page, the choice between the two addresses from the page an empty slot, to try to keep the data in the page order; If no slot is found, select an empty slot on the page near a neighbor. If the two addresses belong to different pages, choose a less used page to balance the usage of each page and maintain the order of data within and between pages. The algorithm can be improved in the following two aspects: 1. When allocating empty slots, point query and range query need to be classified. For point query, the current algorithm can be used, while for range query, the data of a range is read each time, so the algorithm needs to be further optimized or a new algorithm is designed. 2. When empty slots are allocated, several consecutive empty slots can be allocated for each SKV, so that multiple versions of the SKV can be stored in adjacent address space. During CPU prefetching, multiple versions can be prefetched into the cache, which is conducive to the performance of multi-version access.
|  | Write PBRB specific design documents (including data structure design, empty slot allocation strategy design, cache eviction policy design, etc.) | high | big,core issue | Qiang Zhang, Ruida Xu | 2021-05-25 |  | Ongoing | Write PBRB specific design documents, including the following modules: 1.Data structure and data organization of PBRB; 2. Empty slot allocation strategy: how to allocate an empty slot from the PBRB to store data when caching hot data; 3. Eviction policy: when the space usage of PBRB exceeds the threshold, the old data should be evicted, we combining the characteristics of PBRB cache (such as cache with SKV granularity, data management with Page unit) and the advantages and disadvantages of existing eviction policies, design a low cost and high efficiency eviction policy for PBRB cache.
|  | Implementation of basic PBRB algorithm | high | medium | Ruida Xu | 2021-04-09 |  | Ongoing | Implement the basic PBRB algorithm swap-in and swap-out algorithm, and write test examples to verify the correctness of the cache, and prepare for the subsequent combination with Indexer and Plog. current progress: Currently, the existing functions are tested by implementing a simple Schema and Plog. Based on the completed Schema of Chogori, a simple Schema was defined for testing. At the same time, a simple PLog definition is given based on the document to test the basic PBRB function. On the basis of simple Schema, PBRB is realized to obtain Schema information: 1. Obtain the size of Row, the size of nullableBitmap and the relative offset corresponding to each field through Schema information, so as to quickly access the field 2. Calculate the size information of occupancyBitmap based on Schema information and Page information. In PBRB, the process of reading the full row from the simple PLog and assigning it to the empty slot of the PBRB is implemented, but it has not yet been combined with the Indexer interface.
|  | writing test data to compare with current eviction algorithm | high | medium | Ruida Xu | 2021-04-16 |  | Ongoing | Write test data to verify the correctness of PBRB Algorithm
|  | Implement the LRU algorithm in PBRB, and use the test data to compare with PBRB eviction policy | high | medium | Ruida Xu | 2021-04-24 |  | Ongoing | Implement the LRU algorithm, and use the test data to test and compare the two algorithms, and analyze the advantages and disadvantages of the current algorithms.
|  | Combination of PBRB Implementation and Chogori Platform | high | medium | Ruida Xu, Qiang Zhang | 2021-06-01 |  | Ongoing | Read the existing code, and carry out interface design and docking work. Planning work: 1. Study Chogori's existing Schema, Record and Payload codes and integrate them into the code. 2. Combine with the currently implemented Indexer to achieve the goal of maintaining a relatively orderly insert in the design.
|  | Paper writing and submission | high | big | Qiang Zhang | 2021-05-08 |  | Ongoing | From April 1st to May 8th, I will focus on writing and submitting papers.
| Research on Persistent Memory Plog | Research on NVM performance chararistics && Learn chogori's existing design of Plog | high | medium | Zhen Liu | 2021-01-29 | 2021-01-28 | finished | 1. Read the paper: The paper summarizes the use of PM guidance: a.Avoid random accesses smaller than 256B. b. For the transmission of big data, use non-temporal stores instructions to bypass the cache architecture. c. Limit the number of threads that access Optane DIMMs. d. Avoid mixed or multi-threaded access to NUMA nodes. 2. Read Chogori design documents and code: Chogori-Node-Overview.md && code
|  | Keep on learning the NVM architecture ,programming methods Research on some classic works on NVM | high | medium | Zhen Liu | 2021-03-12 | 2021-03-12 | finished | 1. Recent work is mainly to investigate the work of PM optimization, mainly involving the index structure, file system, and file mapping fields. The following is a selection of representative work introductions: a. Variable-length health is widespread in today's applications. The existing persistent B+tree usually uses a simple data model that is a fixed-length health value in order to improve the locality of the cache. Under such assumptions, in order to support Variable-length keys need to add additional data areas in the form of pointers, which usually leads to serious pointer chasing problems. In order to achieve efficient range query performance, ROART uses Radix Tree as the basic data structure, while designing a leaf array structure. The keys under the same cardinality node are placed together in array form to avoid the pointer chasing overhead caused by range query. See ROART@fast21. b. Under the background of PM, because the traditional file system is at the kernel layer, system calls have gradually become the bottleneck of the file system. Therefore, KucoFS designed the file system of the kernel and user layer system. By transferring most of the functions of the kernel layer to the user layer, such as using pmdk to write data in the file system, the file index information is transferred to the user layer to complete the indexing. Bypassing system calls, metadata maintenance is done using feasible threads at the kernel layer to achieve collaboration and improve the performance of the file system. See KucoFS@fast21. c. The high-performance features of PM make the file system on PM perform file mapping 70% of the time. HashFS uses a single hash operation for all mapping and allocation operations, bypassing the file system cache, but through SIMD Parallel prefetch mapping and explicit cache address translation bring significant performance improvement, see HashFS@fast21. 2. Completed some file system-based performance tests on PM equipment in the dax mode of Ext4 file system.
|  | Learn and try to deploy some common engineering projects of PM. | high | medium | Zhen Liu | 2021-04-09 |  | Ongoing | Current Progress: 1. Understand the optimization schemes of existing engineering projects such as redis for PM equipment. a: libmemkind is a general-purpose memory allocator that provides PM-based volatile memory allocation function. Based on this memory allocator, intel has implemented a version of Redis: memKeyDB. This solution uses PM memory, but it is regarded as volatile memory. Persistence is still achieved through the RDB/AOF mechanism, the specific implementation methods and optimization points need to be further investigated b. pmemkv is a lightweight kv storage system implemented by intel based on libpmemobj. It supports multiple data structures as the underlying storage engine. Here we mainly introduce the optimization of B+tree. When writing B+tree, splitting nodes is the most time-consuming Therefore, it is necessary to move the data between the two child nodes, and libpmemobj can provide a swap interface similar to the memory, by exchanging the two data points, the effect of zero copy is achieved, and the amount of data written is greatly reduced.
|  | Learn typical benchmarks tools and development kits on PM device | high | medium | Zhen Liu | 2021-04-09 |  | Ongoing | Curent Progress: 1. For the benchmark test of PM devices, fio is mainly used for file system-based bandwidth, thread count, and access block size tests, intel Memory Lartency Checker is used for latency testing, and filebench is deployed to simulate real application server load testing, and summarized . plan: 1. Have a basic understanding of several libraries in the PMDK development library, mainly to answer questions: what functions can be provided, what performance can be brought, what are the trade-offs, and what are the applicable scenarios. 2. Have a general understanding of the current benchmark tools

## 二、Detailed Progress(GraphStore)
二、Detailed Progress
System | Module | Task | Priority | Workload | responsible personality | Planned completion time | Completion time | Status | Details | Risks | Remarks
Hybrid Memory-Oriented Graph Object Storage System | Background and Motivation of Graph Object Storage System | survey on the proposed Graph database system | medium | big | Shun Zuo | 2021-02-01 | 2020-01-21 | finished
|  | Research the data layout of the graph | high | medium | Mingxiang Lu | 2021-01-25 | 2021-01-25 | finished
| Graph Object Storage | Do research on open graph database | medium | medium | Mingxiang Lu | 2021-03-26 | 2021-03-26 | finished | 1. Read the Geabase paper, and understand the Alibaba database project; 2. Read the official documents of the open source graph database Nebula, understand the open source graph database project Nebula, and deploy it locally; 3. Plan to read the relevant papers of the graph database to understand the research status of graph data in academia and industry in recent years。 |  | 1. The process of converting Graph API to KV layer has not been completed. This part will start in two weeks (4/12) and is planned to be completed in two weeks.
|  | Continue researching current graph database work in industry and academia | medium | medium | Mingxiang Lu | 2021-04-09 |  | ongoing | 1. Retrieved Graph related work (SIDMOD'20 SIGMOD'19, SIGMOD'18, FAST'19, VLDB'21, VLDB'20), overview of relevant paper abstracts, it took about a week; 2. Do research on the industry's database (AWS Neptune), which is a commercial graph database system based on the cloud. It supports both RDF and property graph data models, and plans to understand its storage layer. It will take about a week; 3. Learn about Microsoft's graph database A1 (A1: A Distributed In-Memory Graph Database, SIGMOD'20) by reading graph database papers. A1 is built on the existing distributed platform Farm, and learning from A1 To build a graph application on a storage platform. It takes about a week.