## 一、project description
Project Summary
Project goal | 1. Based on the Chogori platform, a distributed memory Schema-aware KV (SKV) system, evaluate the system performance of the memory tiered architecture and make use of the SKV architecture. 2. Based on the evaluation result, design a efficient single-node full-memory index structure and study its application scenarios. 3. Based on the evaluation result, optimize the object storage system with the hybrid memory architecture and study its application scenarios. 4. Based on the SKV architecture, design the NDP operator acceleration system of the graph storage engine and study its application scenarios.
Project plan
System architecture
Biweekly Overall Progress（from Start - 2021.1.14）
Overall Progress： 1. Survey on the memory index, MVCC, page cache policies, and distributed transaction protocol; 2. Successfully deploy and run Chogori open source project; 3. Preliminarily understand and design how to find an empty slot for the hot row in the PBRB cache. 4. Preliminarily understand where and how index work in Chogori project. 5. Simply learn the plog design framework in chogori. 6. Investigate the data layout of graph and compare with SKV. 7. K23SI transaction optimization about write intent pending. Next Plan： 1. Following the indexer branch, (define a unified interface if necessary), implement the indexer module and integrate the hot trie index (Yirui Lai). 2. Implement a basic PBRB cache, include alocate and reclaim pages, find empty rows from pages, read/insert hot row from/to PBRB and eviction policy (Qiang Zhang and Ruida Xu). 3. Research on persistent Memory and Plog (Zhen Liu) 4. K23SI transaction optimization (Zuo Shun) 5. Graph database survey (How to efficiently use SKV to represent graphs.)(Mingxiang Lu) 6. Implement K23SI transaction optimization schema(Zuo Shun)
Risks & Help-seeking

## 二、Detailed Progress(TxnSystem)
二、Detailed Progress
System | Module | Task | Priority | Workload | responsible personality | Planned completion time | Completion time | Status | Details | Risks | Remarks
distributed transaction system | K23SI protocol | Understand the K23SI transaction protocol. And compares the protocol with spanner | high | big | Shun Zuo | 2020-12-27 | 2020-12-27 | finished
|  | Optimize the RetentionWindow to reduce the memory footprint of Multi-versioned records | low | medium | Shun Zuo | - |  | pending
|  | Optimize the WI of K23SI transaction.The server returns WI_persis_pending after writing WI in the memory | high | big | Shun Zuo | 2021-01-22 | 2021-01-29 | finished | after disscussion in last Friday, the new schema has been proposed, which might need some minor updates/fixs. |  | next two Weeks' plan
|  | Implementation processing write request asynchronously | high | big | Shun Zuo | 2021-03-01 |  | ongoing
SKV module

## 二、Detailed Progress(TieredMem)
二、Detailed Progress
System | Module | Task | Priority | Workload | responsible personality | Planned completion time | Completion time | Status | Details | Risks | Remarks
Distributed Tiered Memory Object System | Single-node full memory index research | survey on the proposed memory indexes and how they implement MVCC. | high | big | Yirui Lai | 2020-12-31 | 2020-12-31 | finished
|  | Design an unified interface for indexer | high | medium | Yirui Lai | 2021-01-29 | 2020-01-28 | finished | based on existing code
|  | optomize the version chain design | medium | medium | Yirui Lai | - |  | pending
|  | integrate HOT index into chogori | high | big | Yirui Lai | 2021-03-01
| Page Based Row Buffer | research on the propsed cache allocation and management policies | high | big | Qiang Zhang | 2020-12-31 | 2020-12-31 | finished
|  | research on the propsed cache eviction policy | high | big | Ruida Xu,Qiang Zhang | 2020-12-31 | 2020-12-31 | Ongoing
|  | Interfaces Definition and Functions Implementation for the PBRB | high | big,core issue | Qiang Zhang, Ruida Xu | 2021-03-01 |  | Ongoing
|  | Design the function to find an empty slot for the hot row in the PBRB cache | high | medium | Qiang Zhang, Ruida Xu | 2021-01-29 | 2020-01-28 | finished | It needs the KVNode of indexer to provide some interfaces
|  | Survey on the detail impelmentation of eviction plicy for typical in-memory KV stores (e.g.,Redis) | high | medium | Ruida Xu, Qiang Zhang | 2021-02-06 |  | Ongoing
| Research on Persistent Memory Plog | Research on NVM performance chararistics && Learn chogori's existing design of Plog | high | medium | Zhen Liu | 2021-01-29 | 2021-01-28 | finished | Read paper: An Empirical Guide to the Behavior and Use of Scalable Persistent Memory Read design docs and code:Chogori-Node-Overview.md && code
|  | Keep on learning the NVM architecture ,programming methods Research on some classic works on NVM | high | medium | Zhen Liu | 2021-02-06 |  | Ongoing

## 二、Detailed Progress(GraphStore)
二、Detailed Progress
System | Module | Task | Priority | Workload | responsible personality | Planned completion time | Completion time | Status | Details | Risks | Remarks
Hybrid Memory-Oriented Graph Object Storage System | Background and Motivation of Graph Object Storage System | survey on the proposed Graph database system | medium | big | Shun Zuo | 2021-02-01 | 2020-01-21 | finished
|  | Research on d Graph's data layout | high | medium | Mingxiang Lu | 2021-01-25 | 2021-01-25 | finished
|  | Embed the existing graph database into the Chogori project | high | big | Mingxiang Lu | 2021-03-01 |  | Ongoing
Graph Object Storage